## Sheet1
1 | 2 |  | 3 |  | 4 | 5 |  | 6 | 7 | 8 | 9 |  | 10 | 11 |  | 12 | 13 | 14 |  | 15 | 16 |  | 17
March |  | 0.2 | April | 0.3 |  |  | 0.4 |  | May |  |  | 0.5 |  | June | 0.6 |  |  |  | 0.7 |  | July | 0.8 |  | Rtur | 10:00 | 11:00 | 0:00 | 13:00 | 14:00
20-24 | 27-31 |  | 3-7 |  | 10-14 | 17-21 |  | 24-28 | 1-5 | 8-12 | 15-19 |  | 22-26 | 29-2 |  | 5-9 | 12-16 | 19-23 |  | 26-30 | 3-7 |  | 10-14 | Francis | 18:30 | 19:30 | 20:30 | 21:30 | 22:30
Deployable base |  |  | Syndication |  | Core blogging |  |  | Admin |  |  |  |  | Authentication |  |  | Hosting site |  |  |  | Subscription |  |  | Catch up
Continues deployment to Windows and Linux servers |  |  | RSS import |  | Posts |  |  | Categories |  |  |  |  | Login |  |  | Sub domains? |  |  |  | PayPal?
Automated publishing Blogifier.Core to Nuget (MyGet) |  |  | RSS display |  | Categories |  |  | Posts |  |  |  |  | Logout
Embedding resources in Blogifier.Core |  |  |  |  | Authors |  |  | Editor |  |  |  |  | Password reset
Core and custom themes with css/styles/images embedded |  |  |  |  | Search |  |  | Time zone |  |  |  |  | Google
Custom widgets (ViewComponents) | [7 empty] | Settings |  |  |  |  | Facebook
| Caching | [6 empty] | Email
| Logging | [6 empty] | Profile
| Application settings | [7 empty] | Photo
| SQL server | [7 empty] | Avatar
| PostgreSQL | [7 empty] | Accounts
Personal (user) settings
Branding |  | 0.2 |  | 0.3 | Blog theme |  | 0.4 | Admin theme |  |  |  | 0.5 | Account login |  | 0.6 | Blogifier.NET site |  |  | 0.7 |  |  | 0.8
Styles
Fonts
Logo
Layouts
Forms
Tables
Fav icon
Responsive
Cards
Designing the Layout of the Admin on Photoshop