## Sheet1
1 | 2 |  | 3 |  | 6 | 7 | 8 | 9 |  | 4 | 5 |  | 10 | 11 |  | 12 | 13 | 14 |  | 15 | 16 |  | 17
March |  | 0.2 | April | 0.3 |  | May |  |  | 0.4 |  |  | 0.5 |  | June | 0.6 |  |  |  | 0.7 |  | July | 0.8 |  | Rtur | 10:00 | 11:00 | 0:00 | 13:00 | 14:00
20-24 | 27-31 |  | 3-7 |  | 10-14 | 17-21 | 24-28 | 1-5 |  | 8-12 | 15-19 |  | 22-26 | 29-2 |  | 5-9 | 12-16 | 19-23 |  | 26-30 | 3-7 |  | 10-14 | Francis | 18:30 | 19:30 | 20:30 | 21:30 | 22:30
Deployable base |  |  | Syndication |  | Admin |  |  |  |  | Core blogging |  |  | Authentication |  |  | Hosting site |  |  |  | Subscription |  |  | Catch up
Continues deployment to Windows and Linux servers |  |  | Caching |  | Categories |  |  |  |  | Posts |  |  | Login |  |  | Sub domains? |  |  |  | PayPal?
Automated publishing Blogifier.Core to Nuget (MyGet) |  |  | Logging |  | Posts |  |  |  |  | Categories |  |  | Logout
Embedding resources in Blogifier.Core |  |  | RSS import |  | Editor |  |  |  |  | Authors |  |  | Password reset
Core and custom themes with css/styles/images embedded |  |  | RSS display |  | Time zone |  |  |  |  | Search |  |  | Google
Custom widgets (ViewComponents) |  |  | PostgreSQL |  | Settings |  |  |  |  | List -> more -> detail |  |  | Facebook
| Application settings |  |  |  | Email
| Personal (user) settings |  |  |  | Profile
| EF in memory |  |  |  |  | Photo
| SQL server |  |  |  |  | Avatar
Accounts
Branding |  | 0.2 |  | 0.3 | Admin theme |  |  |  | 0.4 | Blog theme |  | 0.5 | Account login |  | 0.6 | Blogifier.NET site |  |  | 0.7 |  |  | 0.8
Research | Building layout |  | New layout? |  | Logo
Setting up HTML framework | Adding pages (in process) |  | Continue work on pages |  | Fav icon
Working on Photoshop mockups